## cover
PANCHAYAT RAJ ENGINEERING DEPARTMENT
TIRUPATI DISTRICT
GOVERNMENT PRIORITY BUILDINGS - MGNREGS
AS ON 30.05.2022

## GS
PANCHAYAT RAJ ENGINEERING DEPARTMENT - TIRUPATI DISTRICT
Govt. Priority Works Report - Grama Sachivalayam
As on 30.05.2022
S.No | Const | Mandal | No.of Reported Panchayats | No.of Works | Total Submitted Works | Est Cost Rs in lakhs | Exp Rs in lakhs | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid |  | Second Slab Laid | Finishings | Physically Completed | % of Achievement (PC) |  | Physical |  | Short fall | Financial |  | Short fall
[13 empty] | Present Week | Last Week |  |  |  | Present Week | Last Week | Cumulative Target Upto 30.05.22 | Cumulative Acheivement |  | Cumulative Target | Cumulative Acheivement
1 | a | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Pres Tar | tot tar | prev com | diff | tot achi
1 | Tpt | K V B Puram | 19 | 19 | 19 | 695 | 245.49 | 1 | 0 | 4 | 1 | 1 | 31.5789 | 31.5789 | 1 | 6 | 5 | 26.3158 | 26.3158 | 5 | 1 | 4 |  |  | 0 | 1 | 6 | 6 | -1 | 0
2 | Gdr | Doravarisatram | 10 | 11 | 11 | 425 | 159.82 | 0 | 0 | 2 | 0 | 2 | 36.3636 | 36.3636 | 2 | 2 | 3 | 27.2727 | 27.2727 | 2 | 0 | 2 |  |  | 0 |  | 2 | 8 | -5 | -5
3 | Tpt | Nagalapuram | 10 | 11 | 11 | 435 | 165.98 | 0 | 0 | 1 | 5 | 0 | 54.5455 | 54.5455 | 2 | 0 | 3 | 27.2727 | 27.2727 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 10 | -7 | -7
4 | Tpt | Pakala | 16 | 17 | 17 | 575 | 284.11 | 0 | 1 | 1 | 0 | 4 | 35.2941 | 35.2941 | 2 | 4 | 5 | 29.4118 | 23.5294 | 5 | 2 | 3 |  |  | 0 | 1 | 6 | 5 | 0 | 2
5 | Tpt | Satyavedu | 14 | 16 | 16 | 630 | 212.77 | 0 | 0 | 2 | 2 | 2 | 37.5 | 37.5 | 4 | 1 | 5 | 31.25 | 31.25 | 4 | 2 | 2 |  |  | 0 | 1 | 5 | 5 | 0 | 2
6 | Gdr | Chillakur | 18 | 19 | 19 | 670 | 248.33 | 0 | 0 | 1 | 0 | 2 | 15.7895 | 15.7895 | 7 | 3 | 6 | 31.5789 | 26.3158 | 4 | 3 | 1 |  |  | 0 | 1 | 5 | 5 | 1 | 4
7 | Gdr | Chittamur | 14 | 15 | 15 | 505 | 235.65 | 0 | 0 | 0 | 3 | 0 | 20 | 20 | 5 | 2 | 5 | 33.3333 | 33.3333 | 4 | 2 | 2 |  |  | 0 |  | 4 | 12 | -7 | -5
8 | Tpt | Ramachandrapuram | 11 | 11 | 11 | 405 | 176.44 | 2 | 0 | 0 | 1 | 0 | 9.0909 | 9.0909 | 0 | 4 | 4 | 36.3636 | 36.3636 | 2 | 0 | 2 |  |  | 0 |  | 2 | 3 | 1 | 1
9 | Tpt | Yerpedu | 19 | 19 | 19 | 760 | 373.04 | 0 | 0 | 0 | 0 | 2 | 10.5263 | 10.5263 | 3 | 7 | 7 | 36.8421 | 36.8421 | 6 | 1 | 5 |  |  | 0 | 1 | 7 | 6 | 1 | 2
10 | Gdr | Sullurpeta | 7 | 8 | 8 | 305 | 131.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 | 37.5 | 37.5 | 2 | 2 | 0 |  |  | 0 | 1 | 3 | 5 | -2 | 0
11 | Tpt | Renigunta | 15 | 21 | 21 | 810 | 319.74 | 0 | 3 | 1 | 1 | 2 | 33.3333 | 33.3333 | 5 | 1 | 8 | 38.0952 | 38.0952 | 4 | 1 | 3 |  |  | 0 | 1 | 5 | 6 | 2 | 3
12 | Tpt | Tirupati Rural | 18 | 31 | 31 | 1195 | 622.18 | 0 | 4 | 4 | 0 | 0 | 25.8065 | 25.8065 | 1 | 10 | 12 | 38.7097 | 38.7097 | 7 | 4 | 3 |  |  | 0 | 1 | 8 | 3 | 9 | 13
13 | Gdr | Balayapalle | 15 | 15 | 15 | 590 | 237.89 | 0 | 2 | 1 | 2 | 2 | 46.6667 | 46.6667 | 2 | 0 | 6 | 40 | 40 | 3 | 1 | 2 |  |  | 0 |  | 3 | 6 | 0 | 1
14 | Tpt | Pichatur | 10 | 10 | 10 | 390 | 173.88 | 0 | 2 | 1 | 0 | 0 | 30 | 30 | 1 | 2 | 4 | 40 | 40 | 3 | 1 | 2 |  |  | 0 |  | 3 | 7 | -3 | -2
15 | Tpt | Puttur | 10 | 10 | 10 | 355 | 152.83 | 0 | 0 | 2 | 0 | 1 | 30 | 30 | 2 | 1 | 4 | 40 | 40 | 4 | 1 | 3 |  |  | 0 | 1 | 5 | 6 | -2 | -1
16 | Tpt | Thottambedu | 15 | 16 | 15 | 520 | 173.78 | 0 | 2 | 0 | 2 | 1 | 33.3333 | 33.3333 | 1 | 3 | 6 | 40 | 33.3333 | 4 | 2 | 2 |  |  | 0 | 1 | 5 | 4 | 2 | 4
17 | Gdr | Gudur | 14 | 17 | 17 | 580 | 248.44 | 0 | 0 | 1 | 2 | 2 | 29.4118 | 29.4118 | 4 | 1 | 7 | 41.1765 | 35.2941 | 2 | 1 | 1 |  |  | 0 |  | 2 | 6 | 1 | 2
18 | Gdr | Kota | 13 | 16 | 16 | 610 | 267.06 | 0 | 0 | 2 | 0 | 0 | 12.5 | 12.5 | 6 | 1 | 7 | 43.75 | 37.5 | 2 | 1 | 1 |  |  | 0 | 1 | 3 | 4 | 3 | 4
19 | Gdr | Pellakur | 13 | 13 | 13 | 515 | 275.08 | 0 | 0 | 0 | 0 | 1 | 7.6923 | 7.6923 | 5 | 1 | 6 | 46.1538 | 46.1538 | 2 | 1 | 1 |  |  | 0 | 1 | 3 | 4 | 2 | 3
20 | Gdr | Tada | 14 | 15 | 15 | 600 | 259.93 | 0 | 0 | 0 | 1 | 1 | 13.3333 | 13.3333 | 3 | 3 | 7 | 46.6667 | 46.6667 | 4 | 2 | 2 |  |  | 0 |  | 4 | 4 | 3 | 5
21 | Tpt | Srikalahasti | 19 | 20 | 19 | 745 | 306.86 | 0 | 2 | 0 | 1 | 3 | 31.5789 | 31.5789 | 1 | 3 | 9 | 47.3684 | 47.3684 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 8 | 1 | 2
22 | Tpt | Chinnagottigallu | 10 | 10 | 10 | 385 | 217.02 | 0 | 0 | 1 | 0 | 1 | 20 | 20 | 0 | 3 | 5 | 50 | 50 | 2 | 0 | 2 |  |  | 0 | 1 | 3 | 5 | 0 | 0
23 | Tpt | Vadamalapeta | 12 | 12 | 12 | 455 | 247.96 | 0 | 0 | 0 | 1 | 1 | 16.6667 | 16.6667 | 2 | 2 | 6 | 50 | 50 | 4 | 1 | 3 |  |  | 0 | 1 | 5 | 9 | -3 | -2
24 | Tpt | Chandragiri | 17 | 19 | 19 | 695 | 396.23 | 0 | 1 | 0 | 0 | 3 | 21.0526 | 21.0526 | 1 | 4 | 10 | 52.6316 | 52.6316 | 5 | 3 | 2 |  |  | 0 |  | 5 | 3 | 7 | 10
25 | Gdr | Naidupeta | 11 | 11 | 11 | 390 | 178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 6 | 54.5455 | 54.5455 | 3 | 2 | 1 |  |  | 0 | 1 | 4 | 7 | -1 | 1
26 | Tpt | Buchinaidu Kandriga | 14 | 14 | 14 | 460 | 207.73 | 0 | 1 | 0 | 1 | 2 | 28.5714 | 28.5714 | 0 | 2 | 8 | 57.1429 | 57.1429 | 3 | 2 | 1 |  |  | 0 | 1 | 4 | 5 | 3 | 5
27 | Gdr | Venkatagiri | 11 | 12 | 12 | 455 | 200.94 | 0 | 1 | 1 | 0 | 0 | 16.6667 | 16.6667 | 2 | 1 | 7 | 58.3333 | 58.3333 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 12 | -5 | -5
28 | Gdr | Ojili | 10 | 10 | 10 | 380 | 223.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 60 | 60 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 5 | 1 | 1
29 | Tpt | Narayanavanam | 10 | 11 | 11 | 415 | 208.09 | 0 | 0 | 0 | 0 | 1 | 9.0909 | 9.0909 | 1 | 2 | 7 | 63.6364 | 63.6364 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 6 | 1 | 1
30 | Tpt | Yerravaripalem | 11 | 11 | 11 | 405 | 293.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 8 | 72.7273 | 72.7273 | 1 | 0 | 1 |  |  | 0 |  | 1 | 9 | -1 | -1
31 | Gdr | Vakadu | 11 | 12 | 12 | 455 | 296.98 | 0 | 1 | 0 | 0 | 0 | 8.3333 | 8.3333 | 0 | 2 | 9 | 75 | 75 | 1 | 0 | 1 |  |  | 0 |  | 1 | 10 | -1 | -1
32 | Tpt | Varadaiahpalem | 12 | 13 | 13 | 445 | 284.44 | 0 | 0 | 0 | 0 | 1 | 7.6923 | 7.6923 | 1 | 1 | 10 | 76.9231 | 76.9231 | 1 | 1 | 0 |  |  | 0 |  | 1 | 7 | 3 | 4
33 | Gdr | Dakkili | 14 | 14 | 14 | 535 | 395.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 12 | 85.7143 | 85.7143 | 0 | 0 | 0 |  |  | 0 | 1 | 1 | 7 | 5 | 5
34 | Tpt | Tirupati Urban | 1 | 5 | 5 | 200 | 150.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 100 | 100 | 1 | 2 | -1 |  |  | 0 |  | 1 | 8 | -3 | -1
|  | Total: | 438 | 484 | 482 | 17990 | 8573.24 | 3 | 20 | 25 | 23 | 35 | 21.3693 | 21.37 | 80 | 75 | 221 | 45.8506 | 44.81 | 97 | 40 | 57 | 0 | 0 | 0 | 22 | 119 | 216 | 5 | 45
|  | Previous week: | 438 | 484 | 482 | 17990 | 8573.24 | 3 | 20 | 26 | 22 | 35 | 21.37 | 21.16 | 80 | 80 | 216 | 44.81 | 43.57 | 75 | 35 | 40 | 0 | 0 | 0
|  | Diffrence: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | -0.00070539 |  | 0 | -5 | 5 | 1.0406

## RBK
PANCHAYAT RAJ ENGINEERING DEPARTMENT - TIRUPATI DISTRICT
Govt. Priority Works Report - Rythubarosa Kendrams
As on 30.05.2022
S.No | Const | Mandal | No.of Reported Panchayats | No.of Works | Total Submitted Works | Est Cost Rs in lakhs | Exp Rs in lakhs | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid |  | Second Slab Laid | Finishings | Physically Completed | % of Achievement (PC) |  | Physical |  | Short fall | Financial |  | Short fall
[13 empty] | Present Week | Last Week |  |  |  | Present Week | Last Week | Cumulative Target Upto 30.05.22 | Cumulative Acheivement |  | Cumulative Target | Cumulative Acheivement
1 | a | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Pres Tar | tot tar | prev com | diff | tot achi
1 | Tpt | Puttur | 10 | 10 | 10 | 218 | 48.32 | 2 | 1 | 4 | 0 | 2 | 70 | 70 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 |  |  | 0 | 1 | 3 | 3 | -3 | -3
2 | Tpt | Nagalapuram | 10 | 10 | 10 | 218 | 82.56 | 1 | 0 | 4 | 0 | 1 | 50 | 50 | 0 | 3 | 1 | 10 | 10 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 6 | -5 | -5
3 | Gdr | Chillakur | 18 | 19 | 19 | 414.2 | 102.99 | 0 | 2 | 2 | 3 | 10 | 89.4737 | 89.4737 | 0 | 0 | 2 | 10.5263 | 10.5263 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 1 | 1 | 2
4 | Tpt | Chandragiri | 16 | 16 | 16 | 348.8 | 128.4 | 2 | 1 | 3 | 0 | 6 | 62.5 | 68.75 | 0 | 2 | 2 | 12.5 | 6.25 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 2 | 0 | 1
5 | Gdr | Sullurpeta | 7 | 8 | 8 | 174.4 | 52.5 | 0 | 1 | 1 | 1 | 4 | 87.5 | 87.5 | 0 | 0 | 1 | 12.5 | 0 | 2 | 1 | 1 |  |  | 0 |  | 2 | 6 | -5 | -4
6 | Gdr | Tada | 14 | 15 | 15 | 348.8 | 101.91 | 0 | 2 | 4 | 3 | 4 | 86.6667 | 86.6667 | 0 | 0 | 2 | 13.3333 | 13.3333 | 1 | 0 | 1 |  |  | 0 |  | 1 | 5 | -3 | -3
7 | Tpt | Yerpedu | 19 | 19 | 19 | 414.2 | 117.45 | 1 | 5 | 3 | 0 | 4 | 63.1579 | 68.4211 | 0 | 3 | 3 | 15.7895 | 15.7895 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 5 | -2 | -2
8 | Tpt | Vadamalapeta | 12 | 12 | 12 | 261.6 | 80.24 | 0 | 2 | 3 | 1 | 4 | 83.3333 | 83.3333 | 0 | 0 | 2 | 16.6667 | 16.6667 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 3 | -1 | -1
9 | Gdr | Venkatagiri | 11 | 12 | 12 | 261.6 | 59.43 | 0 | 8 | 0 | 0 | 0 | 66.6667 | 66.6667 | 0 | 2 | 2 | 16.6667 | 16.6667 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 4 | -2 | -1
10 | Tpt | Pakala | 17 | 17 | 17 | 370.6 | 127.47 | 0 | 6 | 1 | 1 | 2 | 58.8235 | 58.8235 | 0 | 4 | 3 | 17.6471 | 17.6471 | 3 | 1 | 2 |  |  | 0 |  | 3 | 5 | -2 | -1
11 | Gdr | Naidupeta | 11 | 11 | 11 | 239.8 | 77.67 | 0 | 0 | 1 | 0 | 8 | 81.8182 | 81.8182 | 0 | 0 | 2 | 18.1818 | 18.1818 | 1 | 0 | 1 |  |  | 0 |  | 1 | 2 | 0 | 0
12 | Tpt | Ramachandrapuram | 11 | 11 | 11 | 239.8 | 60.03 | 2 | 3 | 3 | 0 | 0 | 54.5455 | 54.5455 | 0 | 1 | 2 | 18.1818 | 18.1818 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 1 | 1 | 1
13 | Gdr | Kota | 13 | 16 | 16 | 348.8 | 102.84 | 0 | 0 | 5 | 2 | 5 | 75 | 75 | 0 | 1 | 3 | 18.75 | 12.5 | 1 | 1 | 0 |  |  | 0 |  | 1 | 2 | 1 | 2
14 | Gdr | Balayapalle | 15 | 15 | 15 | 327 | 90.29 | 0 | 6 | 4 | 0 | 1 | 73.3333 | 73.3333 | 0 | 1 | 3 | 20 | 20 | 2 | 0 | 2 |  |  | 0 |  | 2 | 4 | -1 | -1
15 | Tpt | Thottambedu | 15 | 16 | 15 | 327 | 68.25 | 0 | 3 | 4 | 2 | 1 | 66.6667 | 66.6667 | 0 | 2 | 3 | 20 | 20 | 3 | 1 | 2 |  |  | 0 |  | 3 | 5 | -2 | -1
16 | Gdr | Gudur | 14 | 17 | 17 | 370.6 | 122.51 | 0 | 1 | 3 | 2 | 6 | 70.5882 | 70.5882 | 0 | 1 | 4 | 23.5294 | 23.5294 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 3 | 1 | 2
17 | Tpt | K V B Puram | 19 | 19 | 19 | 414.2 | 119.46 | 0 | 6 | 4 | 0 | 0 | 52.6316 | 52.6316 | 0 | 4 | 5 | 26.3158 | 26.3158 | 4 | 1 | 3 |  |  | 0 |  | 4 | 4 | 1 | 2
18 | Gdr | Doravarisatram | 10 | 11 | 11 | 239.8 | 74.35 | 0 | 3 | 1 | 1 | 3 | 72.7273 | 72.7273 | 0 | 0 | 3 | 27.2727 | 27.2727 | 2 | 1 | 1 |  |  | 0 |  | 2 | 6 | -3 | -2
19 | Gdr | Pellakur | 13 | 13 | 13 | 283.4 | 114.51 | 0 | 3 | 1 | 2 | 2 | 61.5385 | 61.5385 | 0 | 1 | 4 | 30.7692 | 30.7692 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 0 | 4 | 4
20 | Tpt | Satyavedu | 13 | 14 | 13 | 283.4 | 79.64 | 0 | 2 | 0 | 4 | 1 | 53.8462 | 53.8462 | 0 | 2 | 4 | 30.7692 | 30.7692 | 2 | 0 | 2 |  |  | 0 |  | 2 | 2 | 2 | 2
21 | Gdr | Chittamur | 14 | 15 | 15 | 327 | 146.53 | 0 | 0 | 1 | 2 | 5 | 53.3333 | 53.3333 | 0 | 2 | 5 | 33.3333 | 33.3333 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 5 | 0 | 0
22 | Tpt | Renigunta | 15 | 17 | 15 | 327 | 105.99 | 0 | 5 | 4 | 0 | 0 | 60 | 60 | 0 | 1 | 5 | 33.3333 | 33.3333 | 4 | 1 | 3 |  |  | 0 |  | 4 | 4 | 1 | 2
23 | Tpt | Varadaiahpalem | 12 | 12 | 12 | 261.6 | 85.44 | 0 | 0 | 5 | 0 | 1 | 50 | 50 | 0 | 2 | 4 | 33.3333 | 33.3333 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 7 | -3 | -2
24 | Gdr | Dakkili | 14 | 14 | 14 | 305.2 | 133.54 | 0 | 1 | 2 | 3 | 0 | 42.8571 | 50 | 0 | 3 | 5 | 35.7143 | 35.7143 | 4 | 1 | 3 |  |  | 0 | 1 | 5 | 0 | 5 | 6
25 | Tpt | Srikalahasti | 18 | 18 | 18 | 392.4 | 165.18 | 0 | 3 | 1 | 1 | 1 | 33.3333 | 33.3333 | 0 | 5 | 7 | 38.8889 | 38.8889 | 4 | 1 | 3 |  |  | 0 |  | 4 | 2 | 5 | 6
26 | Tpt | Tirupati Rural | 5 | 6 | 5 | 109 | 55.28 | 0 | 1 | 0 | 0 | 1 | 40 | 40 | 0 | 1 | 2 | 40 | 40 | 1 | 0 | 1 |  |  | 0 |  | 1 | 3 | -1 | -1
27 | Tpt | Buchinaidu Kandriga | 14 | 14 | 14 | 305.2 | 144.36 | 0 | 1 | 1 | 2 | 0 | 28.5714 | 28.5714 | 0 | 4 | 6 | 42.8571 | 42.8571 | 4 | 1 | 3 |  |  | 0 |  | 4 | 2 | 4 | 5
28 | Tpt | Narayanavanam | 8 | 10 | 8 | 174.4 | 78.37 | 0 | 2 | 0 | 1 | 0 | 37.5 | 37.5 | 0 | 1 | 4 | 50 | 50 | 1 | 1 | 0 |  |  | 0 |  | 1 |  | 4 | 5
29 | Gdr | Ojili | 10 | 10 | 10 | 218 | 93.73 | 0 | 0 | 0 | 0 | 3 | 30 | 40 | 0 | 2 | 5 | 50 | 50 | 1 | 0 | 1 |  |  | 0 |  | 1 | 2 | 3 | 3
30 | Gdr | Vakadu | 11 | 12 | 12 | 261.6 | 140.81 | 0 | 1 | 0 | 1 | 3 | 41.6667 | 41.6667 | 0 | 0 | 7 | 58.3333 | 58.3333 | 2 | 0 | 2 |  |  | 0 |  | 2 | 7 | 0 | 0
31 | Tpt | Chinnagottigallu | 10 | 10 | 10 | 218 | 133.21 | 0 | 0 | 0 | 1 | 2 | 30 | 30 | 0 | 1 | 6 | 60 | 60 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 4 | 2 | 3
32 | Tpt | Pichatur | 10 | 10 | 10 | 218 | 116.32 | 0 | 2 | 0 | 0 | 2 | 40 | 40 | 0 | 0 | 6 | 60 | 60 | 1 | 1 | 0 |  |  | 0 | 1 | 2 | 2 | 4 | 5
33 | Tpt | Yerravaripalem | 11 | 11 | 11 | 239.8 | 131.88 | 1 | 2 | 0 | 0 | 0 | 18.1818 | 18.1818 | 0 | 0 | 8 | 72.7273 | 72.7273 | 3 | 2 | 1 |  |  | 0 |  | 3 | 3 | 5 | 7
34 | Tpt | 2: Tirupati Urban; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0; Last Week 15: 0; Last Week 16: 0; Last Week 17: 0; Cumulative Target Upto 30.05.22 20: 0; Cumulative Acheivement 21: 0 |  | 0 | 8 | -8 | -8
|  | Total: | 420 | 440 | 433 | 9461.2 | 3341.46 | 9 | 73 | 65 | 33 | 82 | 58.4296 | 59.35 | 0 | 50 | 121 | 27.9446 | 27.25 | 80 | 20 | 60 | 0 | 0 | 0 | 15 | 95 | 118 | 3 | 23
|  | Previous week: | 420 | 440 | 433 | 9461.2 | 3341.46 | 9 | 73 | 65 | 34 | 85 | 59.35 | 59.82 | 0 | 49 | 118 | 27.25 | 26.33 | 65 | 17 | 48 | 0 | 0 | 0
|  | Diffrence: | 0 | 0 | 0 |  |  | 0 | 0 | 0 | -1 | -3 | -0.92379 |  | 0 | 1 | 3 | 0.69284 |  |  |  |  | 0 | 0 | 0

## YSR HC
PANCHAYAT RAJ ENGINEERING DEPARTMENT - TIRUPATI DISTRICT
Govt. Priority Works Report - YSR Health Clinics
As on 30.05.2022
S.No | Consti | Mandal | No.of Reported Panchayats | No.of Works | Total Submitted Works | Est Cost Rs in lakhs | Exp Rs in lakhs | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid |  | Second Slab Laid | Finishings | Physically Completed | % of Achievement (PC) |  | Physical |  | Short fall | Financial |  | Short fall
[13 empty] | Present Week | Last Week |  |  |  | Present Week | Last Week | Cumulative Target Upto 30.05.22 | Cumulative Acheivement |  | Cumulative Target | Cumulative Acheivement
1 | a | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Pres Tar | tot tar | prev com | diff | tot achi
1 | Tpt | Puttur | 8 | 8 | 8 | 140 | 24.1 | 2 | 2 | 3 | 0 | 1 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
3 | Tpt | Tirupati Urban | 1 | 5 | 5 | 87.5 | 36.47 | 0 | 1 | 1 | 0 | 0 | 40 | 40 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 3 |  |  | 0 |  | 3 | 0 | 0 | 0
6 | Tpt | Satyavedu | 11 | 14 | 14 | 245 | 41.14 | 0 | 4 | 4 | 2 | 3 | 92.8571 | 92.8571 | 0 | 0 | 1 | 7.1429 | 7.1429 | 4 | 0 | 4 |  |  | 0 | 1 | 5 | 1 | 0 | 0
7 | Gdr | Chillakur | 13 | 13 | 13 | 245 | 66.95 | 0 | 0 | 6 | 5 | 0 | 84.6154 | 84.6154 | 0 | 1 | 1 | 7.6923 | 7.6923 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 1 | 0 | 1
8 | Gdr | Kota | 9 | 12 | 12 | 210 | 63.21 | 0 | 2 | 4 | 1 | 3 | 83.3333 | 91.6667 | 0 | 1 | 1 | 8.3333 | 8.3333 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 1 | 0 | 1
9 | Tpt | Pakala | 11 | 11 | 11 | 192.5 | 45.47 | 0 | 6 | 2 | 0 | 1 | 81.8182 | 81.8182 | 0 | 1 | 1 | 9.0909 | 9.0909 | 2 | 0 | 2 |  |  | 0 |  | 2 | 1 | 0 | 0
10 | Tpt | Renigunta | 15 | 21 | 21 | 367.5 | 86.44 | 0 | 12 | 3 | 0 | 2 | 80.9524 | 80.9524 | 0 | 2 | 2 | 9.5238 | 9.5238 | 1 | 0 | 1 |  |  | 0 | 1 | 2 | 2 | 0 | 0
2 | Gdr | Tada | 9 | 10 | 10 | 192.5 | 40.16 | 0 | 5 | 3 | 1 | 0 | 90 | 90 | 0 | 0 | 1 | 10 | 0 | 3 | 1 | 2 |  |  | 0 |  | 3 | 0 | 1 | 2
4 | Tpt | Chandragiri | 17 | 20 | 20 | 350 | 140.05 | 2 | 3 | 3 | 1 | 5 | 60 | 65 | 0 | 4 | 2 | 10 | 5 | 4 | 2 | 2 |  |  | 0 | 1 | 5 | 1 | 1 | 3
13 | Tpt | Tirupati Rural | 17 | 30 | 30 | 525 | 130.11 | 1 | 15 | 5 | 1 | 3 | 80 | 80 | 0 | 2 | 3 | 10 | 10 | 3 | 2 | 1 |  |  | 0 | 1 | 4 | 3 | 0 | 2
14 | Tpt | Narayanavanam | 8 | 9 | 9 | 157.5 | 39.34 | 0 | 4 | 0 | 1 | 1 | 66.6667 | 66.6667 | 0 | 2 | 1 | 11.1111 | 11.1111 | 2 | 0 | 2 |  |  | 0 |  | 2 | 1 | 0 | 0
15 | Tpt | Vadamalapeta | 9 | 9 | 9 | 157.5 | 39.05 | 1 | 4 | 1 | 0 | 2 | 77.7778 | 77.7778 | 0 | 0 | 1 | 11.1111 | 11.1111 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 1 | 0 | 0
16 | Tpt | Srikalahasti | 16 | 17 | 17 | 297.5 | 72.23 | 2 | 7 | 1 | 2 | 1 | 64.7059 | 64.7059 | 0 | 2 | 2 | 11.7647 | 11.7647 | 2 | 0 | 2 |  |  | 0 |  | 2 | 2 | 0 | 0
5 | Tpt | Yerpedu | 16 | 16 | 16 | 280 | 59.13 | 1 | 5 | 4 | 2 | 2 | 81.25 | 81.25 | 0 | 0 | 2 | 12.5 | 6.25 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 1 | 1 | 2
17 | Tpt | Nagalapuram | 7 | 8 | 8 | 140 | 22.53 | 1 | 5 | 1 | 0 | 0 | 75 | 75 | 0 | 0 | 1 | 12.5 | 12.5 | 1 | 1 | 0 |  |  | 0 | 1 | 2 | 1 | 0 | 1
18 | Gdr | Sullurpeta | 7 | 8 | 8 | 140 | 67.75 | 0 | 1 | 1 | 2 | 3 | 87.5 | 87.5 | 0 | 0 | 1 | 12.5 | 12.5 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 1 | 0 | 1
19 | Tpt | K V B Puram | 15 | 15 | 15 | 262.5 | 73.5 | 0 | 6 | 1 | 2 | 0 | 60 | 60 | 0 | 4 | 2 | 13.3333 | 13.3333 | 2 | 0 | 2 |  |  | 0 |  | 2 | 2 | 0 | 0
20 | Tpt | Thottambedu | 7 | 7 | 7 | 122.5 | 15.45 | 0 | 3 | 2 | 1 | 0 | 85.7143 | 85.7143 | 0 | 0 | 1 | 14.2857 | 14.2857 | 2 | 0 | 2 |  |  | 0 |  | 2 | 1 | 0 | 0
21 | Gdr | Doravarisatram | 11 | 11 | 11 | 192.5 | 69.57 | 0 | 4 | 0 | 3 | 2 | 81.8182 | 81.8182 | 0 | 0 | 2 | 18.1818 | 18.1818 | 2 | 1 | 1 |  |  | 0 | 1 | 3 | 2 | 0 | 1
22 | Gdr | Pellakur | 11 | 11 | 11 | 192.5 | 56.11 | 0 | 4 | 2 | 3 | 0 | 81.8182 | 81.8182 | 0 | 0 | 2 | 18.1818 | 18.1818 | 2 | 0 | 2 |  |  | 0 |  | 2 | 2 | 0 | 0
23 | Gdr | Gudur | 14 | 16 | 16 | 280 | 96.82 | 0 | 3 | 4 | 1 | 4 | 75 | 75 | 0 | 1 | 3 | 18.75 | 18.75 | 1 | 0 | 1 |  |  | 0 |  | 1 | 3 | 0 | 0
11 | Gdr | Chittamur | 10 | 10 | 10 | 175 | 71.83 | 0 | 0 | 4 | 3 | 1 | 80 | 80 | 0 | 0 | 2 | 20 | 10 | 3 | 1 | 2 |  |  | 0 |  | 3 | 1 | 1 | 2
12 | Gdr | Naidupeta | 10 | 10 | 10 | 175 | 51.73 | 0 | 2 | 0 | 1 | 4 | 70 | 70 | 0 | 1 | 2 | 20 | 10 | 3 | 1 | 2 |  |  | 0 |  | 3 | 1 | 1 | 2
24 | Tpt | Ramachandra Puram | 10 | 10 | 10 | 175 | 30.32 | 2 | 3 | 3 | 0 | 0 | 60 | 60 | 0 | 0 | 2 | 20 | 20 | 2 | 0 | 2 |  |  | 0 | 1 | 3 | 2 | 0 | 0
25 | Tpt | Varadaiahpalem | 10 | 10 | 10 | 175 | 31.82 | 0 | 2 | 5 | 1 | 0 | 80 | 80 | 0 | 0 | 2 | 20 | 20 | 3 | 0 | 3 |  |  | 0 | 1 | 4 | 2 | 0 | 0
26 | Gdr | Venkatagiri | 9 | 10 | 10 | 175 | 47.11 | 0 | 7 | 0 | 0 | 0 | 70 | 70 | 0 | 1 | 2 | 20 | 20 | 1 | 1 | 0 |  |  | 0 |  | 1 | 2 | 0 | 1
27 | Tpt | Yerravaripalem | 5 | 5 | 5 | 87.5 | 35.77 | 1 | 1 | 0 | 0 | 1 | 40 | 60 | 0 | 1 | 1 | 20 | 20 | 1 | 1 | 0 |  |  | 0 |  | 1 | 1 | 0 | 1
28 | Gdr | Balayapalle | 14 | 15 | 14 | 262.5 | 59.73 | 0 | 8 | 1 | 0 | 2 | 78.5714 | 78.5714 | 0 | 0 | 3 | 21.4286 | 21.4286 | 1 | 1 | 0 |  |  | 0 |  | 1 | 3 | 0 | 1
29 | Gdr | Dakkili | 7 | 7 | 7 | 122.5 | 47.16 | 0 | 2 | 2 | 0 | 1 | 71.4286 | 71.4286 | 0 | 0 | 2 | 28.5714 | 28.5714 | 1 | 0 | 1 |  |  | 0 |  | 1 | 2 | 0 | 0
31 | Gdr | Ojili | 8 | 8 | 8 | 140 | 63.3 | 0 | 0 | 0 | 0 | 4 | 50 | 50 | 0 | 1 | 3 | 37.5 | 37.5 | 3 | 1 | 2 |  |  | 0 | 1 | 4 | 3 | 0 | 1
30 | Tpt | Chinnagottigallu | 8 | 8 | 8 | 140 | 80.06 | 1 | 1 | 0 | 0 | 1 | 25 | 25 | 0 | 1 | 4 | 50 | 37.5 | 2 | 2 | 0 |  |  | 0 | 1 | 3 | 3 | 1 | 3
32 | Gdr | Vakadu | 7 | 8 | 8 | 157.5 | 73.8 | 0 | 1 | 1 | 1 | 1 | 50 | 50 | 0 | 0 | 4 | 50 | 37.5 | 1 | 2 | -1 |  |  | 0 |  | 1 | 3 | 1 | 3
33 | Tpt | Buchinaidu Kandriga | 12 | 12 | 12 | 210 | 111.69 | 0 | 3 | 0 | 0 | 0 | 25 | 25 | 0 | 3 | 6 | 50 | 41.6667 | 3 | 3 | 0 |  |  | 0 | 1 | 4 | 5 | 1 | 4
34 | Tpt | Pichatur | 4 | 4 | 4 | 70 | 29.77 | 0 | 2 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 2 | 50 | 50 | 0 | 0 | 0 |  |  | 0 |  | 0 | 2 | 0 | 0
|  | Total: | 346 | 388 | 387 | 6842.5 | 2019.67 | 14 | 128 | 67 | 34 | 48 | 71.5762 | 72.35 | 0 | 31 | 65 | 16.7959 | 14.73 | 73 | 24 | 49 | 0 | 0 | 0 | 15 | 85 | 50 | 7 | 28
|  | Previous week: | 346 | 388 | 387 | 6842.5 | 2019.67 | 13 | 132 | 66 | 32 | 50 | 72.35 | 72.87 | 0 | 37 | 57 | 14.73 | 14.21 | 57 | 16 | 41 | 0 | 0 | 0
|  | Diffrence: | 0 | 0 | 0 |  |  | 1 | -4 | 1 | 2 | -2 | -0.77519 |  | 0 | -6 | 8 | 2.0672

## DL
PANCHAYAT RAJ ENGINEERING DEPARTMENT - TIRUPATI DISTRICT
Govt. Priority Works Report - YSR Digital Libraries
As on 30.05.2022
S.No | Const | Mandal | No.of Reported Panchayats | No.of Works | Total Submitted Works | Est Cost Rs in lakhs | Exp Rs in lakhs | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid |  | Second Slab Laid | Finishings | Physically Completed | % of Achievement (PC) |  | Physical |  | Financial |  | Short fall
[13 empty] | Present Week | Last Week |  |  |  | Present Week | Last Week | Cumulative Target Upto 30.05.22 | Cumulative Acheivement | Cumulative Target | Cumulative Acheivement
1 | a | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Gdr | Balayapalle | 3 | 3 | 3 | 48 | 0.01 | 1 | 2 | 0 | 0 | 0 | 66.6667 | 66.6667 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
2 | Tpt | Buchinaidu Kandriga | 24 | 24 | 24 | 384 | 0.01 | 1 | 23 | 0 | 0 | 0 | 95.8333 | 95.8333 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
3 | Tpt | Chandragiri | 33 | 33 | 33 | 528 | 0.06 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
4 | Gdr | Chillakur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
5 | Tpt | Chinnagottigallu | 12 | 12 | 12 | 192 | 0.03 | 1 | 11 | 0 | 0 | 0 | 91.6667 | 91.6667 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
6 | Gdr | Chittamur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
7 | Gdr | Dakkili | 4 | 4 | 4 | 64 | 0.01 | 0 | 4 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
8 | Gdr | Doravarisatram | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
9 | Gdr | Gudur | 14 | 14 | 14 | 224 | 0.03 | 0 | 12 | 2 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
10 | Tpt | K V B Puram | 27 | 27 | 27 | 432 | 0.06 | 5 | 22 | 0 | 0 | 0 | 81.4815 | 81.4815 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
11 | Gdr | Kota | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
12 | Tpt | Nagalapuram | 19 | 19 | 19 | 304 | 0.07 | 17 | 2 | 0 | 0 | 0 | 10.5263 | 10.5263 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
13 | Gdr | Naidupeta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
14 | Tpt | Narayanavanam | 18 | 18 | 18 | 288 | 0.06 | 3 | 15 | 0 | 0 | 0 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
15 | Gdr | Ojili | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
16 | Tpt | Pakala | 28 | 28 | 28 | 448 | 0.06 | 16 | 12 | 0 | 0 | 0 | 42.8571 | 42.8571 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
17 | Gdr | Pellakur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
18 | Tpt | Pichatur | 21 | 21 | 21 | 336 | 0.06 | 0 | 21 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
19 | Tpt | Puttur | 14 | 14 | 14 | 224 | 0.03 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
20 | Tpt | Ramachandra Puram | 23 | 23 | 23 | 368 | 0.11 | 1 | 22 | 0 | 0 | 0 | 95.6522 | 95.6522 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
21 | Tpt | Renigunta | 19 | 19 | 19 | 304 | 0.09 | 16 | 3 | 0 | 0 | 0 | 15.7895 | 15.7895 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
22 | Tpt | Satyavedu | 28 | 28 | 28 | 448 | 0.02 | 4 | 24 | 0 | 0 | 0 | 85.7143 | 85.7143 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
23 | Tpt | Srikalahasti | 42 | 46 | 42 | 736 | 0.08 | 3 | 39 | 0 | 0 | 0 | 92.8571 | 92.8571 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
24 | Gdr | Sullurpeta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
25 | Gdr | Tada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
26 | Tpt | Thottambedu | 6 | 6 | 6 | 96 | 0.01 | 1 | 5 | 0 | 0 | 0 | 83.3333 | 83.3333 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
27 | Tpt | Tirupati Rural | 28 | 28 | 28 | 448 | 0.06 | 5 | 23 | 0 | 0 | 0 | 82.1429 | 82.1429 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
28 | Tpt | Tirupati Urban | 1 | 1 | 1 | 16 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
29 | Tpt | Vadamalapeta | 20 | 20 | 20 | 320 | 0.05 | 0 | 20 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
30 | Gdr | Vakadu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
31 | Tpt | Varadaiahpalem | 26 | 26 | 26 | 416 | 0.05 | 21 | 5 | 0 | 0 | 0 | 19.2308 | 19.2308 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
32 | Gdr | Venkatagiri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
33 | Tpt | Yerpedu | 40 | 40 | 40 | 640 | 0.09 | 14 | 26 | 0 | 0 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
34 | Tpt | Yerravaripalem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  | Total: | 450 | 454 | 450 | 7264 | 1.05 | 157 | 291 | 2 | 0 | 0 | 65.1111 | 65.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Previous week: | 450 | 454 | 450 | 7264 | 1.05 | 157 | 291 | 2 | 0 | 0 | 65.1111 | 65.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Diffrence: | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0

## BMCU
PANCHAYAT RAJ ENGINEERING DEPARTMENT - TIRUPATI DISTRICT
Govt. Priority Works Report - BULK MILK COOLING UNITS
As on 30.05.2022
S.No | Const | Mandal | No.of Reported Panchayats | No.of Works | Total Submitted Works | Est Cost Rs in lakhs | Exp Rs in lakhs | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid |  | Second Slab Laid | Finishings | Physically Completed | % of Achievement (PC) |  | Physical |  | Short fall | Total No of Works sanctioned | Financial |  | Short fall
[13 empty] | Present Week | Last Week |  |  |  | Present Week | Last Week | Cumulative Target Upto 30.05.22 | Cumulative Acheivement |  |  | Cumulative Target | Cumulative Acheivement
1 | a | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Gdr | Balayapalle | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
2 | Tpt | Buchinaidu Kandriga | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 14 |  |  | 0
3 | Tpt | Chandragiri | 1 | 1 | 1 | 17.67 | 2.34 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 16 |  |  | 0
4 | Gdr | Chillakur | 1 | 1 | 1 | 17.67 | 1.76 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
5 | Tpt | Chinnagottigallu | 1 | 1 | 1 | 17.67 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 10 |  |  | 0
6 | Gdr | Chittamur | 1 | 1 | 1 | 17.67 | 1.25 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
7 | Gdr | Dakkili | 1 | 1 | 1 | 17.67 | 1.01 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
8 | Gdr | Doravarisatram | 1 | 1 | 1 | 17.67 | 3.28 | 0 | 0 | 0 | 0 | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
9 | Gdr | Gudur | 1 | 1 | 1 | 17.67 | 0.31 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
10 | Tpt | K V B Puram | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 19 |  |  | 0
11 | Gdr | Kota | 1 | 1 | 1 | 17.67 | 0 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
12 | Tpt | Nagalapuram | 1 | 1 | 1 | 17.67 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 10 |  |  | 0
13 | Gdr | Naidupeta | 1 | 1 | 1 | 17.67 | 0 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
14 | Tpt | Narayanavanam | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 8 |  |  | 0
15 | Gdr | Ojili | 1 | 1 | 1 | 17.67 | 0.7 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
16 | Tpt | Pakala | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 17 |  |  | 0
17 | Gdr | Pellakur | 1 | 1 | 1 | 17.67 | 1.02 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
18 | Tpt | Pichatur | 1 | 1 | 1 | 17.67 | 3.01 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 10 |  |  | 0
19 | Tpt | Puttur | 1 | 1 | 1 | 17.67 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 10 |  |  | 0
20 | Tpt | Ramachandra Puram | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 11 |  |  | 0
21 | Tpt | Renigunta | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 15 |  |  | 0
22 | Tpt | Satyavedu | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 14 |  |  | 0
23 | Tpt | Srikalahasti | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 18 |  |  | 0
24 | Gdr | Sullurpeta | 1 | 1 | 1 | 17.67 | 3.28 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
25 | Gdr | Tada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
26 | Tpt | Thottambedu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 15 |  |  | 0
27 | Tpt | Tirupati Rural | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 4 |  |  | 0
28 | Tpt | Tirupati Urban | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0
29 | Gdr | Vakadu | 1 | 1 | 1 | 17.67 | 5.28 | 0 | 0 | 0 | 0 | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
30 | Tpt | Varadaiahpalem | 1 | 1 | 1 | 17.67 | 2.82 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 1 | 0 | 0 | 0 |  |  | 0 | 12 |  |  | 0
31 | Gdr | Venkatagiri | 0 | 1 | 1 | 17.67 | 0 | 0 | 0 | 1 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 |  |  | 0
32 | Tpt | Yerpedu | 1 | 1 | 1 | 17.67 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 18 |  |  | 0
33 | Tpt | Yerravaripalem | 1 | 1 | 1 | 17.67 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 11
34 | Tpt | Vadamalapeta | 1 | 1 | 1 | 17.67 | 12.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100 | 100 |  |  | 0 | 12 |  |  | 0
|  | Total: | 29 | 30 | 30 | 530.1 | 46.17 | 3 | 15 | 7 | 0 | 2 | 80 | 83.33 | 0 | 2 | 1 | 3.3333 | 3.33 | 1 | 0 | 1 | 257 | 0 | 0 | 0
|  | Previous week: | 29 | 30 | 30 | 530.1 | 46.17 | 3 | 15 | 7 | 0 | 3 | 83.3333 | 83.33 | 0 | 1 | 1 | 3.3333 | 3.33 | 1 | 0 | 0 | 257 | 0 | 0 | 0
|  | Diffrence: | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | -1 | -3.3333 |  | 0 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0

## Div
DIVISION WISE PERFORMANCE
Govt. Priority Buildings Reports - PR Circle, Tirupati
Dt 30.05.2022
S.No | Type of Building | Mandal | Division | No.of Reported Panchayats | No.of Works | Est Cost Rs in lakhs | Exp Rs in lakhs 07.05.22 | Total Submitted Works | Not Staretd | Below Basement Level | Basement Level | Roof Level | Roof Laid | % from BBL to GF slab Laid | Second Slab Laid | Finishings | Physically Completed | Agency Problem | Court case | School Premises | Site Problem | Proposed for Cancellation & Other Problems | % of Achievement (PC) | Cumulative Target Upto 21.05.22 | Cumulative Acheivement | Short fall | Remarks
1 | 2 | 3 |  | 4 | 5 | 6 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | Grama Sachivalayam | Total | Tirupati | 263 | 296 | 10975 | 5213.48 | 294 | 3 | 16 | 17 | 15 | 25 | 24.8299 | 29 | 58 | 131 | 14 | 8 | 2 | 4 |  | 44.5578 | 66 | 25 | 41
|  |  | Gudur | 175 | 188 | 7015 | 3359.76 | 188 | 0 | 4 | 8 | 8 | 10 | 15.9574 | 51 | 17 | 90 | 5 | 1 |  |  |  | 47.8723 | 31 | 15 | 16
| Total: |  |  | 438 | 484 | 17990 | 8573.24 | 482 | 3 | 20 | 25 | 23 | 35 | 21.3693 | 80 | 75 | 221 | 19 | 9 | 2 | 4 | 0 | 45.8506 | 97 | 40 | 57
2 | Rythubarosa Kendram | Total | Tirupati | 245 | 252 | 5341 | 1927.85 | 245 | 9 | 45 | 40 | 13 | 28 | 51.4286 | 0 | 37 | 73 | 43 | 5 | 0 | 9 |  | 29.7959 | 49 | 13 | 36
|  |  | Gudur | 176 | 188 | 4120.2 | 1413.61 | 188 | 0 | 28 | 25 | 20 | 54 | 67.5532 | 0 | 13 | 48 | 30 | 1 |  |  |  | 25.5319 | 31 | 7 | 24
| Total: |  |  | 421 | 440 | 9461.2 | 3341.46 | 433 | 9 | 73 | 65 | 33 | 82 | 58.4296 | 0 | 50 | 121 | 73 | 6 | 0 | 9 | 0 | 27.9446 | 80 | 20 | 60
3 | YSR Health Clinics | Total | Tirupati | 208 | 239 | 4182.5 | 1144.44 | 239 | 14 | 89 | 39 | 13 | 23 | 68.6192 | 0 | 25 | 36 | 55 | 7 | 0 | 13 |  | 15.0628 | 43 | 12 | 31
|  |  | Gudur | 140 | 149 | 2660 | 875.232 | 148 | 0 | 39 | 28 | 21 | 25 | 76.3514 | 0 | 6 | 29 | 43 | 1 |  |  | 3 | 19.5946 | 30 | 12 | 18
| Total: |  |  | 348 | 388 | 6842.5 | 2019.672 | 387 | 14 | 128 | 67 | 34 | 48 | 71.5762 | 0 | 31 | 65 | 98 | 8 | 0 | 13 | 3 | 16.7959 | 73 | 24 | 49
4 | YSR Digital Libraries | Total | Tirupati | 428 | 433 | 6928 | 1 | 429 | 156 | 273 | 0 | 0 | 0 | 63.6364 | 0 | 0 | 0 | 81 | 1 | 4 | 53 | 45 | 0 | 0 | 0 | 0
|  |  | Gudur | 21 | 21 | 336 | 0.05 | 21 | 1 | 18 | 2 | 0 | 0 | 95.2381 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total: |  |  | 449 | 454 | 7264 | 1.05 | 450 | 157 | 291 | 2 | 0 | 0 | 65.1111 | 0 | 0 | 0 | 101 | 1 | 4 | 53 | 45 | 0 | 0 | 0 | 0
5 | Bulk Milk Cooling Units | Total | Tirupati | 17 | 17 | 300.39 | 28.28 | 17 | 3 | 10 | 1 | 0 | 0 | 64.7059 | 0 | 2 | 1 | 0 |  |  | 1 |  | 5.8824 | 1 | 0 | 1
|  |  | Gudur | 12 | 13 | 229.71 | 17.89 | 13 | 0 | 5 | 6 | 0 | 2 | 100 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Total: |  |  | 29 | 30 | 530.1 | 46.17 | 30 | 3 | 15 | 7 | 0 | 2 | 80 | 0 | 2 | 1 | 8 | 0 | 0 | 2 | 0 | 3.3333 | 1 | 0 | 1
| District Total: |  |  | 1685 | 1796 | 42087.8 | 13981.592 | 1782 | 186 | 527 | 166 | 90 | 167 | 53.3109 | 80 | 158 | 408 | 299 | 24 | 6 | 81 | 48 | 22.8956 | 251 | 84 | 167

## Sheet1 (hidden)
| GSB |  |  | RBK |  |  | YSR HC |  |  | YSR DL |  |  | BMCU
Balayapalle | 46.6667 | 6 | 40 | 73.3333 | 3 | 20 | 78.5714 | 3 | 21.4286 | 66.6667 | 0 | 0 | 100 | 0 | 0
Buchinaidu Kandriga | 28.5714 | 8 | 57.1429 | 28.5714 | 6 | 42.8571 | 25 | 5 | 41.6667 | 95.8333 | 0 | 0 | 100 | 0 | 0
Chandragiri | 21.0526 | 10 | 52.6316 | 68.75 | 1 | 6.25 | 65 | 1 | 5 | 0 | 0 | 0 | 100 | 0 | 0
Chillakur | 15.7895 | 5 | 26.3158 | 89.4737 | 2 | 10.5263 | 84.6154 | 1 | 7.6923 | 0 | 0 | 0 | 100 | 0 | 0
Chinnagottigallu | 20 | 5 | 50 | 30 | 6 | 60 | 25 | 3 | 37.5 | 91.6667 | 0 | 0 | 0 | 0 | 0
Chittamur | 20 | 5 | 33.3333 | 53.3333 | 5 | 33.3333 | 80 | 1 | 10 | 0 | 0 | 0 | 100 | 0 | 0
Dakkili | 0 | 12 | 85.7143 | 50 | 5 | 35.7143 | 71.4286 | 2 | 28.5714 | 100 | 0 | 0 | 100 | 0 | 0
Doravarisatram | 36.3636 | 3 | 27.2727 | 72.7273 | 3 | 27.2727 | 81.8182 | 2 | 18.1818 | 0 | 0 | 0 | 100 | 0 | 0
Gudur | 29.4118 | 6 | 35.2941 | 70.5882 | 4 | 23.5294 | 75 | 3 | 18.75 | 100 | 0 | 0 | 100 | 0 | 0
K V B Puram | 31.5789 | 5 | 26.3158 | 52.6316 | 5 | 26.3158 | 60 | 2 | 13.3333 | 81.4815 | 0 | 0 | 100 | 0 | 0
Kota | 12.5 | 6 | 37.5 | 75 | 2 | 12.5 | 91.6667 | 1 | 8.3333 | 0 | 0 | 0 | 100 | 0 | 0
Nagalapuram | 54.5455 | 3 | 27.2727 | 50 | 1 | 10 | 75 | 1 | 12.5 | 10.5263 | 0 | 0 | 0 | 0 | 0
Naidupeta | 0 | 6 | 54.5455 | 81.8182 | 2 | 18.1818 | 70 | 1 | 10 | 0 | 0 | 0 | 100 | 0 | 0
Narayanavanam | 9.0909 | 7 | 63.6364 | 37.5 | 4 | 50 | 66.6667 | 1 | 11.1111 | 83.3333 | 0 | 0 | 100 | 0 | 0
Ojili | 0 | 6 | 60 | 40 | 5 | 50 | 50 | 3 | 37.5 | 0 | 0 | 0 | 100 | 0 | 0
Pakala | 35.2941 | 4 | 23.5294 | 58.8235 | 3 | 17.6471 | 81.8182 | 1 | 9.0909 | 42.8571 | 0 | 0 | 100 | 0 | 0
Pellakur | 7.6923 | 6 | 46.1538 | 61.5385 | 4 | 30.7692 | 81.8182 | 2 | 18.1818 | 0 | 0 | 0 | 100 | 0 | 0
Pichatur | 30 | 4 | 40 | 40 | 6 | 60 | 50 | 2 | 50 | 100 | 0 | 0 | 100 | 0 | 0
Puttur | 30 | 4 | 40 | 70 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ramachandrapuram | 9.0909 | 4 | 36.3636 | 54.5455 | 2 | 18.1818 | 60 | 2 | 20 | 95.6522 | 0 | 0 | 100 | 0 | 0
Renigunta | 33.3333 | 8 | 38.0952 | 60 | 5 | 33.3333 | 80.9524 | 2 | 9.5238 | 15.7895 | 0 | 0 | 100 | 0 | 0
Satyavedu | 37.5 | 5 | 31.25 | 53.8462 | 4 | 30.7692 | 92.8571 | 1 | 7.1429 | 85.7143 | 0 | 0 | 100 | 0 | 0
Srikalahasti | 31.5789 | 9 | 47.3684 | 33.3333 | 7 | 38.8889 | 64.7059 | 2 | 11.7647 | 92.8571 | 0 | 0 | 0 | 0 | 0
Sullurpeta | 0 | 3 | 37.5 | 87.5 | 0 | 0 | 87.5 | 1 | 12.5 | 0 | 0 | 0 | 100 | 0 | 0
Tada | 13.3333 | 7 | 46.6667 | 86.6667 | 2 | 13.3333 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thottambedu | 33.3333 | 5 | 33.3333 | 66.6667 | 3 | 20 | 85.7143 | 1 | 14.2857 | 83.3333 | 0 | 0 | 0 | 0 | 0
Tirupati Rural | 25.8065 | 12 | 38.7097 | 40 | 2 | 40 | 80 | 3 | 10 | 82.1429 | 0 | 0 | 100 | 0 | 0
Tirupati Urban | 0 | 5 | 100 |  |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vadamalapeta | 16.6667 | 6 | 50 | 83.3333 | 2 | 16.6667 | 77.7778 | 1 | 11.1111 | 100 | 0 | 0 | 0 | 1 | 100
Vakadu | 8.3333 | 9 | 75 | 41.6667 | 7 | 58.3333 | 50 | 3 | 37.5 | 0 | 0 | 0 | 100 | 0 | 0
Varadaiahpalem | 7.6923 | 10 | 76.9231 | 50 | 4 | 33.3333 | 80 | 2 | 20 | 19.2308 | 0 | 0 | 100 | 0 | 0
Venkatagiri | 16.6667 | 7 | 58.3333 | 66.6667 | 2 | 16.6667 | 70 | 2 | 20 | 0 | 0 | 0 | 100 | 0 | 0
Yerpedu | 10.5263 | 7 | 36.8421 | 68.4211 | 3 | 15.7895 | 81.25 | 1 | 6.25 | 65 | 0 | 0 | 100 | 0 | 0
Yerravaripalem | 0 | 8 | 72.7273 | 18.1818 | 8 | 72.7273 | 60 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 21.37 | 216 | 44.81 | 59.35 | 118 | 27.25 | 72.35 | 57 | 14.73 | 65.11 | 0 | 0 | 83.3333 | 1 | 3.3333